## Techniques
Factors Affecting Estimation | Estimation Approaches/Techniques | Miscellenous
Size of System | 3 Point | Root Cause Analysis
Types of Testing | Historical | Heat Map
Scripted Testing | Function Point | Analytics
Exploratory Testing | Delphi Method | Defect Prediction
Supporting/Management Activities | WBS-Work Breakdown Structure | Vertical Traceability
No of Test Cycles | Expert Judgement | Horizontal Traceability
No of Test Environments
Domain Knowledge

## Manual Estimates
SNO | High Level Activities | Activity Breakup | Sub Activities | Efforts
1 | Test Planning | Knowledge Transfer | 1.Application Knowedge 2.Application Landscape 3.Available Document Repository | 30%
|  | Requirement Gathering | 1.Kick off Meetings 2.Brainstorming Sessiosn 3.Reviews/Clarifications
|  | Test Scenario Creation | 1.Create High Level Scenarios
|  | Test Plan Creation | 1.Identify StakeHolders 2.Identify Target Test Environments 3.Finalize Test case Entry/Exit Criteria 4.Identify Tools required 5.Finalise Reporting method/matrices 6.Identify roles & responsibilities of team members 7.Identify Risks 8.Identify Dependencies 9.Formulate Contingency plan 10.Test Strategy 11.Create Test Scedule 12.Assign Testers 13.Identify Training Requirements 14.Identify Test Matrices for Reporting 15.Test Plan Review 16.Update Test Plan
2 | Test Designing | Test Case Creation | 1.Create Test Cases 2.Assign Business Priority | 30%
|  | Test Case Reviews | 1.Review Test Case 2.Update Test Case
|  | Test Management | 1.Create Traceability Matrix 2.Upload Test Case in Repository
|  | Co-Ordination | 1.Review Meetings
3 | Test Execution | Test Execution | 1.Prepare Test Environment 2.Execute Test Case 3.Update Test Case Status | 35%
|  | Maintenance | 1.Update Test Case 2.Update Test Plan
|  | Reporting | 1.Log Defects 2.Track Defects to Closure 3.No of Open Defects/Cycle 4.No of Test Case Executed
4 | Micellenous | Baselines | 1.Baseline Test Execution Productivity 2.Baseline Test Design Productivity | 5%

## Tools
Functional Testing | Performance Testing | CI/CD | Build Tools | Security Testing | Services Testing | Mobile | DevOPS | Test Management | Source Code Management
Selenium | Loadrunner | Jenkins | Maven | OWASP | SOAP-UI | Appium | Nagios | ALM | GitHub
UFT | Jmeter | Team City | ANT |  | Microservices | SeeTest | Jenkins | Test Link | SVN
Tosca |  | Bamboo | Gradle |  |  | Perfecto | Dockers | Jira
Sikuli |  | GitLab CI |  |  |  | AWS | GIT
Eggplant | [5 empty] | BrowserStack
Selenium Grid Hub

## Automation Estimates
Complexity | Low | Medium | High | Maintenance Effort | Ramp Up Efforts | Milestones
1 Test Case Automation | 4hrs | 6hr | 8hr | 15-25% | 1-2 Weeks
Complexity Definitions | No of Screens | No of Validations
Low | 2-4 Screens | Upto 5 Validations
Medium | 4--6 | 6-10 Validations
High | 6-10 Screens | 11-20 Validations