## Tools
Functional Testing | Performance Testing | CI/CD | Build Tools | Security Testing | Services Testing | Mobile | DevOPS | Test Management | Source Code Management
Selenium | Loadrunner | Jenkins | Maven | OWASP | SOAP-UI | Appium | Nagios | ALM | GitHub
UFT | Jmeter | Team City | ANT |  | Microservices | SeeTest | Jenkins | Test Link | SVN
Tosca |  | Bamboo | Gradle |  |  | Perfecto | Dockers | Jira
Sikuli |  | GitLab CI |  |  |  | AWS | GIT
Eggplant | [5 empty] | BrowserStack
Selenium Grid Hub

## Techniques
Techniques | Estimation Techniques
Root Cause Analysis | 3 Point
Heat Map | Historical
Analytics | Function Point
Defect Prediction

## Estimates
SNO | High Level Activities | Activity Breakup | Sub Activities | Efforts
1 | Test Planning | Knowledge Transfer | 1.Application Knowedge 2.Application Landscape 3.Available Document Repository | 30%
|  | Requirement Gathering | 1.Meetings/Brainstorming Sessiosn 2.Reviews/Clarifications
|  | Test Scenario Creation | 1.Create High Level Scenarios
|  | Test Plan Creation | 1.Identify StakeHolders 2.Identify Target Test Environments 3.Finalize Test case entry/exit Criteria 4.Identify Tools required 5.Finalise Reporting method/matrices 6.Identify roles & responsibilities of team members 7.Identify Risks 8.Identify Dependencies 9.Formulate Contingency plan
2 | Test Designing | Test Case Creation | 1.Create Test Cases 2.Assign Business Priority | 30%
|  | Test Case Reviews | 1.Review Test Case 2.Update Test Case
|  | Test Management | 1.Create Traceability Matrix 2.Upload Test Case in Repository
|  | Co-Ordination | 1.Review Meetings
3 | Test Execution | Test Execution | 1.Prepare Test Environment 2.Execute Test Case 3.Update Test Case Status | 35%
|  | Maintenance | 1.Update Test Case 2.Update Test Plan
|  | Reporting | 1.Log Defects 2.Track Defects to Closure 3.No of Open Defects/Cycle 4.No of Test Case Executed
4 | Micellenous | Baselines | 1.Baseline Test Execution Productivity 2.Baseline Test Design Productivity | 5%